## Project milestones
Project 3 | GOAL IS 100/100
Team Members:
Eder Ortiz | Data creation and gathering ¦ Coding | Technology Field | Data Networks
Geraldine Valencia | Data gathering and analysis | Banking Industry | Advisor¦ Engineering background
Demilade Adenuga | Data Analysis and presentation¦ Storytelling | Accounting Field | Consultant
Relevant Modules: | Module 10 - Module 14 ¦
Suggestions on Timing:
Revise | Apr 17th [9:30 - 11:00PM Toronto time] Thursday
Submission | April 19th [6:30 - 9:30 PM Toronto time] Saturday | Submitting April 21st
Project Milestones |  | Planned Date | Start Date | Status | Completion Date
Project Planning |  | 2025-04-08 | 2025-04-10 | Complete | 2025-04-10
Select Dataset | Choose the data you are interested in or the data easier to work with to achieve this assignment. | 2025-04-08 | 2025-04-08 | Complete | 2025-04-08
Review Dataset |  | 2025-04-10 | 2025-04-10 | Complete | 2025-04-11
Create Repository | One team member to create¦include git ignore & READ ME | 2025-04-10 | 2025-04-08 | Complete | N/A
Data Cleaning & Database |  | 2025-04-10 | 2025-04-14 | Complete | 2025-04-15
Analysis/ Data visualizations | Pandas/ Matplotlib/Numpy/Seaborn / API/Flask/Folium | 2025-04-12 | 2025-04-15 | Complete | 2025-04-19
Testing/Results |  | 2025-04-15 | 2025-04-15 | Complete | 2025-04-19
Documentation of analysis and results | This will be added to presentation deck | 2025-04-15 | 2025-04-15 | Complete | 2025-04-19
Combination of codes | Combining all codes | 2025-04-16 | 2025-04-15 | Complete | 2025-04-19
Presentation Deck - 5/6 pager
Share presentation across all the members | All team members will present, turn on our cameras | 2025-04-17 | 2025-04-19 | Complete | 2025-04-21
READ ME File | A nice READ ME file that tells the overview | 2025-04-17 | 2025-04-17 | Complete | 2025-04-21
Submission |  | 2025-04-19 | 2025-04-21 | Complete | 2025-04-21
Project Guidelines
Have different jupyter Notebooks | Ensure we have separate notebooks for each activity with data anlaysis
Then copy all jupyter notebooks into one