## Project milestones
Project 3 | GOAL IS 100/100
Team Members:
Eder Ortiz | Data creation and gathering ¦ Coding | Technology Field | Data Networks
Geraldine Valencia | Data gathering and analysis | Banking Industry | Advisor¦ Engineering background
Demilade Adenuga | Data Analysis and presentation¦ Storytelling | Accounting Field | Consultant
Relevant Modules: | Module 9 - Module 15 ¦
Suggestions on Timing:
Revise | Apr 17th [9:30 - 11:00PM Toronto time] Thursday
Submission | April 19th [6:30 - 9:30 PM Toronto time] Saturday
Days and Plan for each day till April 19th
Project Milestones |  | Planned Date | Start Date | Status | Completion Date
Project Planning |  | 2025-04-08 | 2025-04-10 | In progress
Select Dataset | Choose the data you are interested in or the data easier to work with to achieve this assignment. | 2025-04-08 | 2025-04-08 | Complete | 2025-04-08 | Next week
Review Dataset |  | 2025-04-10
Create Repository | One team member to create¦include git ignore & READ ME | 2025-04-10 | 2025-04-08
Data Cleaning & Database | What is the overarching theme - 2 major points | 2025-04-10
Analysis/ Data visualizations | Pandas/ Matplotlib/Numpy/Seaborn / API/Flask/Folium | 2025-04-12
Testing/Results |  | 2025-04-15
Documentation of analysis and results | This will be added to presentation deck | 2025-04-15
Combination of Jupyter notebook | Combining all analysis into one jupyter notebook | 2025-04-16
Presentation Deck - 5/6 pager | 2 major points will determine the flow of the deck and the storyline | 2025-04-16
Share presentation across all the members | All team members will present, turn on our cameras | 2025-04-17
READ ME File | A nice READ ME file that tells the overview | 2025-04-17
Submission |  | 2025-04-19
Project Guidelines
Have different jupyter Notebooks | Ensure we have separate notebooks for each activity with data anlaysis
Then copy all jupyter notebooks into one